## PMR 1ST SEM 2026.
DEP ED-SCHOOLS DIVISION OF ESCALANTE CITY Procurement Monitoring Report as of JUNE 2026
Code | Procurement Project | End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Fund | ABC |  |  | Contract Cost |  |  | List of Observers | Remarks (Explaining changes in the APP) | Supplier | Status of Payment
|  |  |  | Pre-Procurement Meeting | Posting | Pre-Bid Conference | Eligibility Check | Bid Opening | Bid Evaluation | Post Qualification | Notice of Award | Contract Signing or PO | Notice to Proceed | Delivery | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO
AS PER APP FY 2026
| PROCUREMENT OF ADDITIONAL SUPPLIES FOR THE PASIDUNGOG SA ESCALANTE CITY CY 2025 | OSDS | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 07, 2026 |  | JANUARY 08, 2026 | JANUARY 08, 2026 | GoP | 5600 | 5600 |  | 5600 | 5600 |  |  |  | MFR MARKETING | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE ORIENTATION ON REPUBLIC ACT 12009 "THE NEW GOVERNMENT PROCUREMENT ACT" | OSDS | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 12, 2026 |  | JANUARY 22, 2026 | JANUARY 22, 2026 | GoP | 90000 | 90000 |  | 90000 | 90000 |  |  |  | MOMMY VINE'S CUISINE | PAID
| PROCUREMENT OF TARPAULIN FOR THE ORIENTATION ON REPUBLIC ACT 12009 "THE NEW GOVERNMENT PROCUREMENT ACT" | OSDS | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 12, 2026 |  | JANUARY 20, 2026 | JANUARY 20, 2026 | GoP | 1000 | 1000 |  | 1000 | 1000 |  |  |  | POXEL GRAPHICS AND APPAREL | UNPAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE COA-DBM JC NO. 2024-1, JANUARY 30, 2024 "REVISED MANUAL DISPOSAL OF GOVERNMENT | OSDS | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 12, 2026 |  | MARCH 05, 2026 | MARCH 05, 2026 | GoP | 16800 | 16800 |  | 16800 | 16800 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF SUPPLIES FOR THE CONDUCT OF 2026 DIVISION FESTIVAL OF TALENTS (HISTO-POP CONTEST) | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 12, 2026 |  | FEBRUARY 16, 2026 | FEBRUARY 16, 2026 | GoP | 2840 | 2840 |  | 2840 | 2840 |  |  |  | MFR MARKETING | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF 2026 DIVISION FESTIVAL OF TALENS (HISTO-POP CONTEST) | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 16, 2026 |  | FEBRUARY 18, 2026 | FEBRUARY 18, 2026 | GoP | 10060 | 10060 |  | 10060 | 10060 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF SNACKS FOR THE CONDUCT OF 2026 DIVISION BIBLE MONTH CULMINATION | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 12, 2026 |  | JANUARY 30, 2026 | JANUARY 30, 2026 | GoP | 7000 | 7000 |  | 7000 | 7000 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF SUPPLIES FOR THE CONDUCT OF 2026 DIVISION BIBLE MONTH CULMINATION | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 12, 2026 |  | JANUARY 29, 2026 | JANUARY 29, 2026 | GoP | 5190 | 5190 |  | 5190 | 5190 |  |  |  | MFR MARKETING | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE 2026 DIVISION FESTIVAL OF TALENTS (TECHNOLYMPICS) FOR ELEMENTARY AND SECONDARY | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 02, 2026 |  | FEBRUARY 19, 2026 | FEBRUARY 19, 2026 | GoP | 16800 | 16800 |  | 16800 | 16800 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF SUPPLIES FOR THE 2026 DIVISION FESTIVAL OF TALENTS (TECHNOLYMPICS) FOR ELEMENTARY AND SECONDARY | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 02, 2026 |  | FEBRUARY 18, 2026 | FEBRUARY 18, 2026 | GoP | 15980 | 15980 |  | 15980 | 15980 |  |  |  | MFR MARKETING | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF OCCULAR INSPECTION BY THE PROVINCIAL SCREENING COMMITTEE | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 16, 2026 |  | JANUARY 19, 2026 | JANUARY 19, 2026 | GoP | 12000 | 12000 |  | 12000 | 12000 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE FINANCE STAFF CONFERENCE AND ONLINE ENGAGEMENT TO THE 39TH NATIONAL SEMINAR-WORKSHOP ON THE CONSOLIDATION OF FINANCIAL YEAR-END REPORTS (CY 2025) | OSDS | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 27, 2026 |  | FEBRUARY 12, 2026 | FEBRUARY 12, 2026 | GoP | 41976 | 41976 |  | 41976 | 41976 |  |  |  | DISHTURB CATERING SERVICES | PAID
| PROCUREMENT OF SUPPLIES FOR THE WORKSHOP ON THE ENHANCEMENT AND CONTEXTUALIZATION OF ILLUSTRATIONS OF TRANSITION LEARNING RESOURCES FOR THE IMPLEMENTATION OF MATATAG CURRICULUM | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 19, 2026 |  | JANUARY 23, 2026 | JANUARY 23, 2026 | GoP | 9474 | 9474 |  | 9474 | 9474 |  |  |  | MFR MARKETING | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE DIVISION CAPACITY BUILDING FOR SCHOOL HEADS (PROJECT SHINE) | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 28, 2026 |  | FEBRUARY 4, 2026 FEBRUARY 13, 2026 FEBRUARY 20, 2026 FEBRUARY 27, 2026 MARCH 6, 2026 MARCH 13, 2026 | FEBRUARY 4, 2026 FEBRUARY 13, 2026 FEBRUARY 20, 2026 FEBRUARY 27, 2026 MARCH 6, 2026 MARCH 13, 2026 | GoP | 107500 | 107500 |  | 107500 | 107500 |  |  |  | DISHTURB CATERING SERVICES | PAID
| PROCUREMENT OF SUPPLIES FOR THE CONDUCT OF 2026 DIVISION KINDERGARTEN FESTIVAL | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 27, 2026 |  | FEBRUARY 16, 2026 | FEBRUARY 16, 2026 | GoP | 8430 | 8430 |  | 8430 | 8430 |  |  |  | MFR MARKETING | PAID
| PROCUREMENT OF SNACKS FOR THE CONDUCT OF 2026 DIVISION KINDERGARTEN FESTIVAL | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | JANUARY 27, 2026 |  | FEBRUARY 20, 2026 | FEBRUARY 20, 2026 | GoP | 8250 | 8250 |  | 8250 | 8250 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE DIVISION JOURNALISM CLINIQUING FOR THE QUALIFIERS OF THE 2026 REGIONAL SCHOOLS PRESS CONFERENCE (RSPC) | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 04, 2026 |  | FEBRUARY 16, 2026 | FEBRUARY 16, 2026 | GoP | 41000 | 41000 |  | 41000 | 41000 |  |  |  | DISHTURB CATERING SERVICES | PAID
| PROCUREMENT OF SUPPLIES FOR THE DIVISION JOURNALISM CLINIQUING FOR THE QUALIFIERS OF THE 2026 REGIONAL SCHOOLS PRESS CONFERENCE (RSPC) | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 05, 2026 |  | FEBRUARY 9, 2026 | FEBRUARY 9, 2026 | GoP | 1200 | 1200 |  | 1200 | 1200 |  |  |  | MFR MARKETING | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE ELECTION OF SELG/SSLG FEDERATED OFFICERS FOR S.Y. 2026-2027 | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 20, 2026 |  | FEBRUARY 24, 2026 | FEBRUARY 24, 2026 | GoP | 35000 | 35000 |  | 35000 | 35000 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF SUPPLIES FOR THE ELECTION OF SELG/SSLG FEDERATED OFFICERS FOR S.Y. 2026-2027 | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 20, 2026 |  | FEBRUARY 23, 2026 | FEBRUARY 23, 2026 | GoP | 4435 | 4435 |  | 4435 | 4435 |  |  |  | MFR MARKETING | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE ORIENTATION-WORKSHOP OF SCHOOL HEADS FOR THE PREPARATION OF DOCUMENTS FOR THE PRC ACCREDITATION OF INSET | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 20, 2026 |  | FEBRUARY 25, 2026 | FEBRUARY 25, 2026 | GoP | 16000 | 16000 |  | 16000 | 16000 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE FIRST DIVISION CONVERGENCE OF EDUCATION LEADERS (DCEL) 2026 | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 17, 206 |  | FEBRUARY 19, 2026 | FEBRUARY 19, 2026 | GoP | 25200 | 25200 |  | 25200 | 25200 |  |  |  | MOMMY VINE'S CUISINE | PAID
| PROCUREMENT OF SNACKS FOR THETURNOVER CEREMONY OF PEER TUTORING KITS AND MONOBLOC CHAIRS IN PARTNERSHIP WITH THE CHURCH OF THE LATTER-DAY SAINTS' | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 10, 2026 |  | FEBRUARY 19, 2026 | FEBRUARY 19, 2026 | GoP | 4350 | 4350 |  | 4350 | 4350 |  |  |  | JENNY'S LUTONG BAHAY | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE ORIENTATION-WORKSHOP ON THE IMPLEMENTATION OF THE STRENGTHENED SENIOR HIGH SCHOOL PROGRAM (SSHSP) FOR NON-IMPLEMENTING SCHOOLS | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 20, 2026 |  | FEBRUARY 23, 2026 | FEBRUARY 23, 2026 | GoP | 24000 | 24000 |  | 24000 | 24000 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF PRINTING AND BINDING OF FULLER CHART | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | APRIL 16, 2026 |  | JUNE 22, 2026 | JUNE 22, 2026 | GoP | 94700 | 94700 |  | 94700 | 94700 |  |  |  | LINE EDGE GRAPHICS DESIGN SERVICES | ONGOING
| PROCUREMENT OF MEALS AND SNACKS FOR THE HRMPSB AND SUBCOMMITTEE MEMBERS FOR THE CONDUCT OF EVALUATION OF DEMONSTRATION TEACHING OF TEACHER APPLICANTS FOR SY 2026-2027 | OSDS | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MARCH 02, 2026 |  | MARCH 04, 2026 MARCH 05, 2026 | MARCH 04, 2026 MARCH 05, 2026 | GoP | 52500 | 52500 |  | 52500 | 52500 |  |  |  | DISHTURB CATERING SERVICES | PAID
| PROCUREMENT OF ICT EQUIPMENT FOR MAINTENANCE AND REPAIR | OSDS | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MARCH 10, 2026 |  | APRIL 08, 2026 | APRIL 08, 2026 | GoP | 40000 | 40000 |  | 10000 | 10000 |  |  |  | CHRISDAN OFFICE AND SCHOOL SUPPLIES | PAID
| PROCUREMENT OF SAFE AND POTABLE WATER FOR SDO ESCALANTE CITY PERSONNEL | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MARCH 18, 2026 |  | March 23, 2026 March 30, 2026 April 06, 2026 April 13, 2026 April 16, 2026 April 20, 2026 April 23, 2026 April 30, 2026 May 6, 2026 May 11, 2026 | March 23, 2026 March 30, 2026 April 06, 2026 April 13, 2026 April 16, 2026 April 20, 2026 April 23, 2026 April 30, 2026 May 6, 2026 May 11, 2026 | GoP | 18720 | 18720 |  | 18720 | 18720 |  |  |  | H2OK | ONGOING
| PROCUREMENT OF SECURITY SERVICES | OSDS | Small Value Procurement |  | MARCH 13, 2026 |  |  | MARCH 17, 2026 |  |  |  | MARCH 19, 2026 |  | APRIL 30, 2026 | APRIL 30, 2026 | GoP | 230000 | 230000 |  | 228000 | 228000 |  |  |  | STANDSTILL SECURITY AGENCY | ONGOING
| PROCUREMENT OF MEALS AND SNACKS FOR THE WORKSHOP ON THE SUBMISSION OF DIVISION BUDGET PROPOSALS FOR CY 2027 | OSDS | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | March 30, 2026 |  | DAY 1 - MARCH 10, 2026 DAY 2 - MARCH 11, 2026 DAY 3 - MARCH 12, 2026 DAY 4 - MARCH 13, 2026 | DAY 1 - MARCH 10, 2026 DAY 2 - MARCH 11, 2026 DAY 3 - MARCH 12, 2026 DAY 4 - MARCH 13, 2026 | GoP | 41480 | 41480 |  | 41480 | 41480 |  |  |  |  | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF THE DIVISION ADVOCACY PITCH CONTEST | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MARCH 11, 2026 |  | MARCH 18, 2026 | MARCH 18, 2026 | GoP | 3996 | 3996 |  | 3996 | 3996 |  |  |  | DISHTURB CATERING SERVICES | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE CELEBRATION OF NATIONAL ARTS MONTH (PAGMUGNA 2026) | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 23, 2026 |  | FEBRUARY 26, 2026 | FEBRUARY 26, 2026 | GoP | 9000 | 9000 |  | 9000 | 9000 |  |  |  | JENNY'S LUTONG BAHAY | PAID
| PROCUREMENT OF SUPPLIES FOR THE CELEBRATION OF NATIONAL ARTS MONTH (PAGMUGNA 2026) | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 23, 2026 |  | FEBRUARY 25, 2026 | FEBRUARY 25, 2026 | GoP | 3050 | 3050 |  | 3050 | 3050 |  |  |  | MFR MARKETING | PAID
| PROCUREMENT OF SERVICES (FILMING EQUIPMENT RENTALS) FOR THE PEACE SHORT FILM PRODUCTION | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MARCH 10, 2026 |  | MARCH 13, 2026 | MARCH 13, 2026 | GoP | 12500 | 12500 |  | 12500 | 12500 |  |  |  | SOUNDCRAFTPRO MULTIMEDIA SERVICES | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE PEACE SHORT FILM PRODUCTION | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MARCH 06, 2026 |  | March 10, 2026 March 11, 2026 March 12, 2026 March 14, 2026- Complete Delivery | March 10, 2026 March 11, 2026 March 12, 2026 March 14, 2026 |  | 18400 | 18400 |  | 18400 | 18400 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF SNACKS FOR THE CONDUCT OF NATIONAL WOMEN'S MONTH | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MARCH 05, 2026 |  | MARCH 09, 2026 | MARCH 09, 2026 | GoP | 8000 | 8000 |  | 8000 | 8000 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF CAKES FOR THE SDO PERSONNEL BIRTHDAY CELEBRANT | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [8 empty] | MARCH 25, 2026 | MARCH 25, 2026 | GoP | 15000 | 15000 |  | 15000 | 15000 |  |  |  | NELENE CATERING SERVICES | UNPAID
| PROCUREMENT OF OFFICE SUPPLIES (PS-DBM DEPOT) | OSDS | Agency to Agency |  | NOT POSTED - AGENCY TO AGENCY | [6 empty] | MARCH 16, 2026 |  | PARTIAL 1ST - MAY 14, 2026 | PARTIAL 1ST - MAY 14, 2026 | GoP | 116855.14 | 116855.14 |  | 116855.14 | 116855.14 |  |  |  | PROCUREMENT SERVICES | ONGOING DELIVERY
| PROCUREMENT OF OFFICE SUPPLIES (NOT AVAILABLE IN PS-DBM DEPOT) | OSDS | Small Value Procurement |  | MARCH 20, 2026 |  |  | MARCH 24, 2026 |  |  |  | MARCH 26, 2026 |  | JULY 18, 2026 | JULY 18, 2026 | GoP | 383144.86 | 383144.86 |  | 356740.7 | 356740.7 |  |  |  | JT & SONS TRADING CORPORATION | UNPAID
| REPAIR AND MAINTENANCE OF TRANSPORT VEHICLE | OSDS | Direct Contracting |  | NOT POSTED - DIRECT CONTRACTING | [6 empty] | MARCH 17, 2026 |  | May 2026 | May 2026 | GoP | 88000 | 88000 |  | 27524.11 | 27524.11 |  |  |  | TOYOTA NEGROS OCCIDENTAL, INC. | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE DEVELOPMENT OF SCHOOL INITIATED DROPOUT REDUCTION INTERVENTION (SIDRIS) 2026 | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MARCH 19, 2026 |  | FOR IMPLEMENTATION | FOR IMPLEMENTATION | GoP | 26600 | 26600 |  | 26600 | 26600 |  |  |  | NELENE CATERING SERVICES | UNPAID
| PROCUREMENT OF ADVOCACY SHIRT FOR THE DEVELOPMENT OF SCHOOL INITIATED DROPOUT REDUCTION INTERVENTION (SIDRIS) 2026 | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MARCH 23, 2026 |  | APRIL 15, 2026 | APRIL 15, 2026 | GoP | 6860 | 6860 |  | 6860 | 6860 |  |  |  | POXEL GRAPHICS AND APPARELS PRINTING SERVICES | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF DIVISION CONVERGENCE OF EDUCATIONAL LEADERS (DCEL) | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MARCH 09, 2026 |  | MARCH 26, 2026 | MARCH 26, 2026 | GoP | 25200 | 25200 |  | 25200 | 25200 |  |  |  |  | Partially Paid
| PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF THE PRESENTATION OF STRATEGIC AND IMPLEMENTATION PLAN ON THE STRENGTHENED SENIOR HIGH SCHOOL PROGRAMS (SSHSP) | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | FEBRUARY 20, 2026 |  | APRIL 07, 2026 | APRIL 07, 2026 | GoP | 18000 | 18000 |  | 18000 | 18000 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF TARPAULIN FOR THE CONDUCT OF DIVISION PROGRAM IMPLEMENTATION REVIEW OF ARAL READING PROGRAM AND ARAL-NUMERACY PLANNING | CID | Small Value Procurement |  | APRIL 13, 2026 |  |  | APRIL 17, 2026 |  |  |  | APRIL 07, 2026 |  | APRIL 21, 2026 | APRIL 21, 2026 | GoP | 1080 | 1080 |  | 960 | 960 |  |  |  | RONZ AND CHEL PRINTING SERVICES | UNPAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF DIVISION PROGRAM IMPLEMENTATION REVIEW OF ARAL READING PROGRAM AND ARAL-NUMERACY PLANNING | CID | Small Value Procurement |  | NOT POSTED - SMALL VALUE PROCUREMENT (4/13/26) |  |  | APRIL 17, 2026 |  |  |  | APRIL 17, 2026 |  | APRIL 21, 2026 | APRIL 21, 2026 | GoP | 70400 | 70400 |  | 59136 | 59136 |  |  |  | RONZ AND CHEL PRINTING SERVICES | PAID
| PROCUREMENT OF SNACKS FOR THE CONDUCT OF CAPACITY BUILDING ON THE UTILIZATION OF PROGRAM MANAGEMENT INFORMATION SYSTEM (PMIS) | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | APRIL 06, 2026 |  | APRIL 13, 2026 | APRIL 13, 2026 | GoP | 14400 | 14400 |  | 14400 | 14400 |  |  |  | JENNY'S LUTONG BAHAY | PAID
| PROCUREMENT OF SNACKS AND CAKES FOR THE CONDUCT OF GENDER-SENSITIVE RECOGNITIOON OF ACHIEVEMENTS INCLUDING BIRTHDAYS OF SDO PERSONNEL, SPIRITUAL, HEALTH AND WELLNESS | SGOD | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MARCH 19, 2026 |  | MARCH 25, 2026 | MARCH 25, 2026 | GoP | 15000 | 15000 |  | 15000 | 15000 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE FIRST QUARTER DIVISION PROGRAM IMPLEMENTATION REVIEW AND PERFORMANCE ASSESSMENT (DPIRPA) FOR CY 2026 | SGOD | Small Value Procurement |  | APRIL 20, 2026 |  |  | APRIL 23, 2026 |  |  |  | APRIL 24, 2026 |  | APRIL 28, 2026 | APRIL 28, 2026 | GoP | 18000 | 18000 |  | 14800 | 14800 |  |  |  | MOMMY VINE'S CUISINE | PAID
| PROCUREMENT OF ESSENTIAL MEDICINES | SGOD | Small Value Procurement |  | MAY 7, 2026 |  |  | MAY 12, 2026 |  |  |  | MAY 15, 2026 |  | JUNE 08, 2026 | JUNE 08, 2026 | GoP | 7551.99 | 7551.99 |  | 7551.99 | 7551.99 |  |  |  | ELLEMARIE PHARMACY | PAID
| PROCUREMENT OF SNACKS FOR THE CONDUCT OF NATIONAL ROLL-OUT OF THE INSIGHTED MOBILE APPLICATION | SGOD | Small Value Procurement | [8 empty] | APRIL 10, 2026 |  | APRIL 14, 2026 | APRIL 14, 2026 | GoP | 8550 | 8550 |  | 8550 | 8550 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF DEWORMING TABLETS FOR SCHOOL-BASED FEEDING PROGRAM (SBFP) | SGOD | Small Value Procurement |  | MAY 7, 2026 |  |  | MAY 12, 2026 |  |  |  | MAY 15, 2026 |  | Not yet Delivered | Not yet Delivered | GoP | 37100 | 37100 |  | 29574 | 29574 |  |  |  | PJK YADAH CORPORATION | NOT YET DELIVERED
| PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE REPAIR OF MALE AND FEMALE COMFORT ROOMS AT SCHOOLS DIVISION OFFICE OF ESCALANTE CITY | SGOD | Small Value Procurement |  | APRIL 24, 2026 |  |  | APRIL 29, 2026 |  |  |  | MAY 04, 2026 |  | JULY 16, 2026 | JULY 16, 2026 | GoP | 104485 | 104485 |  | 99085 | 99085 |  |  |  | T & SONS TRADING CORPORATION | UNPAID
| PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE RELOCATION AND EXTENSION OF DIVISION CANOPY OF SCHOOLS DIVISION OFFICE OF ESCALANTE CITY | SGOD | Small Value Procurement |  | APRIL 24, 2026 |  |  | APRIL 29, 2026 |  |  |  | MAY 04, 2026 |  | JUNE 15, 2026 | JUNE 15, 2026 | GoP | 53333.33 | 53333.33 |  | 44758 | 44758 |  |  |  | MCD ENTERPRISE AND GENERAL MERCHANDISE | PAID
| PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE REPAIR OF COMFORT ROOMS AND ROOFING OF GABRIELA HALL AT OLD SCHOOLS DIVISION OFFICE OF ESCALANTE CITY | SGOD | Small Value Procurement |  | APRIL 24, 2026 |  |  | APRIL 29, 2026 |  |  |  | MAY 04, 2026 |  | JULY 16, 2026 | JULY 16, 2026 | GoP | 58835 | 58835 |  | 56830 | 56830 |  |  |  | T & SONS TRADING CORPORATION | UNPAID
| PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE EXTENSION OFFICE FOR DIVISION PAYROLL UNIT, INSTALLATION OF DRYWALL AND PARTITION AT SHN AND PROCUREMENT OFFICE | SGOD | Small Value Procurement |  | APRIL 24, 2026 |  |  | APRIL 29, 2026 |  |  |  | MAY 04, 2026 |  | 1ST - JUNE 4, 2026 2ND - JUNE 14, 2026 3RD - JULY 16, 2026 | 1ST - JUNE 4, 2026 2ND - JUNE 14, 2026 3RD - JULY 16, 2026 | GoP | 64220 | 64220 |  | 62840 | 62840 |  |  |  | T & SONS TRADING CORPORATION | UNPAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF ORIENTATION ON LEARNING SYSTEMS REFORM POLICIES FOR OTHER DIVISION OFFICE PERSONNEL AND SCHOOL HEADS | CID | Small Value Procurement |  |  |  |  | APRIL 27, 2026 |  |  |  | APRIL 28, 2026 |  | APRIL 29, 2026 | APRIL 29, 2026 | GoP | 31200 | 31200 |  | 27000 | 27000 |  |  |  | NELENE CATERING SERVICES |  | LESSO
| PROCUREMENT OF MEALS AND SNACKS FOR THE DIVISION CONVERGENCE OF EDUCATION LEADERS (DCEL) 2026 | SGOD | Small Value Procurement |  | APRIL 30, 2026 |  |  | MAY 11, 2026 |  |  |  | MAY 12, 2026 |  | MAY 13, 2026 - FIRST DELIVERY JULY 07, 2026 - SECOND DELIVERY | MAY 13, 2026 JULY 07, 2026 | GoP | 266400 | 266400 |  | 215550 | 215550 |  |  |  | NELENE CATERING SERVICES | ONGOING
| PROCUREMENT OF MATERIALS FOR THE INSTALLATION OF WATER LINES | OSDS | Small Value Procurement |  | MAY 7, 2026 |  |  | MAY 12, 2026 |  |  |  | MAY 15, 2026 |  | JUNE 15, 2026 | JUNE 15, 2026 | GoP | 4077.6 | 4077.6 |  | 3833 | 3833 |  |  |  | MCD ENTERPRISE AND GENERAL MERCHANDISE | PAID
| PROCUREMENT OF SUPPLIES AND MATERIALS FOR PISA-LIKE RELATED ACTIVITIES | SGOD | Small Value Procurement |  | MAY 7, 2026 |  |  | MAY 12, 2026 |  |  |  | MAY 15, 2026 |  | MAY 26, 2026 | MAY 26, 2026 | GoP | 3840.5 | 3840.5 |  | 3428 | 3428 |  |  |  | MFR MARKETING | UNPAID
| PROCUREMENT OF UNIFORM FOR THE PARTICIPATION TO THE 66TH PALARONG PAMBANSA | OSDS | Small Value Procurement |  | MAY 12, 2026 |  |  | MAY 15, 2026 |  |  |  | MAY 18, 2026 |  | MAY 22, 2026 | MAY 22, 2026 | GoP | 22300 | 22300 |  | 22300 | 22300 |  |  |  | POXEL GRAPHICS AND APPAREL | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF ORIENTATION AND CAPACITY BUILDING IN THE UTILIZATION OF MATH MANIPULATIVES FOR KEY STAGE I LEARNERS | CID | Small Value Procurement |  | MAY 12, 2026 |  |  | MAY 18, 2026 |  |  |  | MAY 20, 2026 |  | JUNE 13, 2026 JUNE 20, 2026 | JUNE 13, 2026 JUNE 20, 2026 | GoP | 59400 | 59400 |  | 45342 | 45342 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF MEALS AND SNACKS FOR DIVISION TRAINING FOR EARLY LANGUAGE LITERACY AND NUMERACY (ELLN) ON THE SCIENCE OF READING (SOR) | CID | Small Value Procurement |  | MAY 21, 2026 |  |  | MAY 25, 2026 |  |  |  | MAY 26, 2025 |  | JUNE 05, 2026 | JUNE 05, 2026 | GoP | 126900 | 126900 |  | 109980 | 109980 |  |  |  | MOMMY VINE'S CUISINE | PAID
| PROCUREMENT OF SERVICES (RENTAL OF VENUE) FOR DIVISION TRAINING FOR EARLY LANGUAGE LITERACY AND NUMERACY (ELLN) ON THE SCIENCE OF READING (SOR) | CID | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION | [6 empty] | MAY 21, 2026 |  | JUNE 05, 2026 | JUNE 05, 2026 | GoP | 28000 | 28000 |  | 28000 | 28000 |  |  |  | EPSTEMPCO-VISAYAS | PAID
| PROCUREMENT OF LEARNING TOOLS AND EQUIPMENT FOR THE GAME-RELATED SCIENCE AND MATH EQUIPMENT | CID | Small Value Procurement |  | MAY 12, 2026 |  |  | MAYy 15, 2026 |  |  |  | MAY 26, 2026 |  | JULY 1, 2026 | JULY 1, 2026 | GoP | 109873 | 109873 |  | 109873 | 109873 |  |  |  | MFR MARKETING | UNPAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE CURRICULUM INNOVATION WRITESHOP IN LITERACY AND NUMERACY | CID | Small Value Procurement |  | MAY 7, 2026 |  |  | MAY 12, 2026 |  |  |  | MAY 15, 2026 |  | MAY 20, 2026 | MAY 20, 2026 | GoP | 94000 | 94000 |  | 85200 | 85200 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF SUPPLIES FOR THE CURRICULUM INNOVATION WRITESHOP IN LITERACY AND NUMERACY | CID | Small Value Procurement |  | MAY 7, 2026 |  |  | MAY 12, 2026 |  |  |  | MAY 15, 2026 |  | MAY 18, 2026 | MAY 18, 2026 | GoP | 1000 | 1000 |  | 1000 | 1000 |  |  |  | MFR MARKETING | PAID
| PROCUREMENT OF SNACKS FOR THE CONDUCT OF INSIGHTED MOBILE APPLICATION | SGOD | Small Value Procurement |  | APRIL 30, 2026 |  |  | MAY 6, 2026 |  |  |  | MAY 06, 2026 |  | MAY 07, 2026 | MAY 07, 2026 | GoP | 9600 | 9600 |  | 7704 | 7704 |  |  |  | NELENE CATERING SERVICES | PAID
| PROCUREMENT OF SNACKS FOR THE DIVISION PEACE INITIATIVE: PROMOTING EQUITY, AWARENESS, CARE, AND EMPOWERMENT | SGOD | Small Value Procurement |  | APRIL 27, 2026 |  |  | APRIL 30, 2026 |  |  |  | MAY 01, 2026 |  | MAY 04, 2026 | MAY 04, 2026 | GoP | 13000 | 13000 |  | 12220 | 12220 |  |  |  | DISHTURB CATERING SERVICES | UNPAID
| PROCUREMENT OF VEGETABLE SEEDS AND ASSORTED GARDEN TOOLS TO BENEFECIARY SCHOOLS OF SDO ESCALANTE CITY | SGOD | Small Value Procurement |  | MAY 7, 2026 |  |  | MAY 12, 2026 |  |  |  | MAY 15, 2026 |  | JULY 1, 2026 | JULY 1, 2026 | GoP | 75000 | 75000 |  | 75000 | 75000 |  |  |  | MFR MARKETING | UNPAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE DIVISION TRAINING OF TEACHERS ON THE REVISED GRADES 6, 9, AND 10 CURRICULUM | SGOD | Small Value Procurement |  | MAY 20, 2026 |  |  | MAY 25, 2026 |  |  |  | MAY 25, 2026 |  | MAY 27, 2026 MAY 28, 2026 MAY 29, 2026 JUNE 02, 2026 | MAY 27, 2026 MAY 28, 2026 MAY 29, 2026 JUNE 02, 2026 | GoP | 1048000 | 1048000 |  | 901280 | 901280 |  |  |  | NELENE CATERING SERVICE | PAID
| PROCUREMENT OF TRAINING MATERIALS FOR THE DIVISION TRAINING OF TEACHERS ON THE REVISED GRADES 6, 9, AND 10 CURRICULUM | SGOD | Small Value Procurement |  | MAY 20, 2026 |  |  | MAY 25, 2026 |  |  |  | MAY 25, 2026 |  | PARTIAL - MAY 27, 2026 PARTIAL - JUNE 04, 2026 PARTIAL - JUNE 15, 2026 | MAY 27, 2026 JUNE 04, 2026 JUNE 15, 2026 | GoP | 202800 | 202800 |  | 166060 | 166060 |  |  |  | JT AND SONS TRADING CORPORATION | UNPAID
| PROCUREMENT OF MEALS FOR THE CONDUCT OF DIVISION BRIGADA ESKWELA KICK OFF | SGOD | Small Value Procurement |  | MAY 20, 2026 |  |  | MAY 25, 2026 |  |  |  | MAY 26, 2026 |  | JUNE 01, 2026 | JUNE 01, 2026 | GoP | 16800 | 16800 |  | 13580 | 13580 |  |  |  | NELENE CATERING SERVICE | PAID
| PROCUREMENT OF TARPAULIN FOR THE CONDUCT OF DIVISION BRIGADA ESKWELA KICK OFF | SGOD | Small Value Procurement |  | MAY 20, 2026 |  |  | MAY 25, 2026 |  |  |  | MAY 26, 2026 |  | JUNE 01, 2026 | JUNE 01, 2026 | GoP | 2000 | 2000 |  | 1600 | 1600 |  |  |  | RONZ & CHEL PRINTING SERVICES | UNPAID
| PROCUREMENT OF MEALS AND SNACKS FOR IMPLEMENTATION OF THE SCHOOL-BASED FEEDING PROGRAM | SGOD | Small Value Procurement |  | MAY 26, 2026 |  |  | JUNE 01, 2026 |  |  |  | JUNE 03, 2026 |  | JUNE 11, 2026 - FIRST DELIVERY | JUNE 11, 2026 | GoP | 100000 | 100000 |  | 84000 | 84000 |  |  |  | MOMMY VINES CUISINE | ONGOING
| PROCUREMENT OF ESSENTIAL SUPPLIES AND MATERIALS FOR SBFP ADVOCACY ACTIVITIES | SGOD | Small Value Procurement |  | MAY 26, 2026 |  |  | JUNE 01, 2026 |  |  |  | JUNE 03, 2026 |  | JULY 06, 2026 | JULY 06, 2026 | GoP | 204447 | 204447 |  | 193900 | 193900 |  |  |  | A.V.S MEDICAL EQUIPMENT TRADING | UNPAID
| PROCUREMENT OF MULTIVITAMINS WITH ZINC (250 ML) FOR SBFP BENEFECIARIES | SGOD | Small Value Procurement |  | MAY 26, 2026 |  |  | JUNE 01, 2026 |  |  |  | JUNE 03, 2026 |  | JUNE 18, 2026 | JUNE 18, 2026 | GoP | 100000 | 100000 |  | 98750 | 98750 |  |  |  | ELLEMARIE PHARMACY | PAID
| PROCUREMENT OF ICT EQUIPMENT FOR MAINTENANCE AND REPAIR | OSDS | Small Value Procurement |  | JUNE 04, 2026 |  |  | JUNE 08, 2026 |  |  |  | JUNE 10, 2026 |  | JUNE 18, 2026 | JUNE 18, 2026 | GoP | 10000 | 10000 |  | 9551.39 | 9551.39 |  |  |  | CHRISDAN OFFICE AND SCHOOL SUPPLIES | PAID
| PROCUREMENT OF ADVOCACY MATERIALS FOR ALS SY 2025-2026 | CID | Small Value Procurement |  | JUNE 04, 2026 |  |  | JUNE 08, 2026 |  |  |  | JUNE 10, 2026 |  | JULY 8, 2026 | JULY 8, 2026 | GoP | 8671 | 8671 |  | 6780 | 6780 |  |  |  | POXEL GRAPHICS AND APPAREL | UNPAID
| PROCUREMENT OF READING MATERIALS FOR KEY STAGE 1 ( KINDERGARTEN TO GRADE 3) | CID | Small Value Procurement |  | JUNE 18, 2026 |  |  | JUNE 23, 2026 |  |  |  | JUNE 25, 2026 |  | NOT YET DELIVERED |  | GoP | 1130100 | 1130100 |  | 939565.8 | 939565.8 |  |  |  | J.C PALABAY ENTERPRISES
| PRODUCTION AND DISTRIBUTION OF DIAGNOSTIC ASSESSMENT MATERIALS | CID | Small Value Procurement |  | JUNE 17, 2026 |  |  | JUNE 23, 2026 |  |  |  | JUNE 25, 2026 |  | NOT YET DELIVERED |  | GoP | 1106029 | 1106029 |  | 1022180 | 1022180 |  |  |  | J.C PALABAY ENTERPRISES
| PROCUREMENT OF DIVISION WEBSITE HOSTING AND SERVICES | OSDS | Direct Acquisition |  | NOT POSTED - DIRECT ACQUISITION |  |  | N/A |  |  |  | JUNE 11, 2026 |  | JUNE 25, 2026 | JUNE 25, 2026 | GoP | 30000 | 30000 |  | 30000 | 30000 |  |  |  | FEGLIX IT SOLUTIONS | UNPAID
| PROCUREMENT OF MEALS FOR THE PARTNERSHIP CONFERENCE WITH BRIGHAM YOUNG UNIVERSITY | SGOD | Small Value Procurement |  | JUNE 05, 2026 |  |  | JUNE 08, 2026 |  |  |  | JUNE 09, 2026 |  | JUNE 11, 2026 | JUNE 11, 2026 | GoP | 4500 | 4500 |  | 4500 | 4500 |  |  |  | NELENE CATERING SERVICE | UNPAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE ORIENTATION OF SCHOOL HEADS ON LESSON PLANNING AND LEARNING DESIGN, CLASSROOM ASSESSMENT, RECOGNITION FOR K TO 12 BASIC EDUCATION AND INSTRUCTIONAL SUPERVISION | SGOD | Small Value Procurement |  | JUNE 11, 2026 |  |  | JUNE 17, 2026 |  |  |  | JUNE 17, 2026 |  | JUNE 18, 2026 | JUNE 18, 2026 | GoP | 26660 | 26660 |  | 23560 | 23560 |  |  |  | MOMMY VINES CUISINE | UNPAID
| PROCUREMENT OF SNACKS FOR THE CONDUCT OF INCLUSIVE CELEBRATION: A GENDER-SENSITIVE PROGRAM ON HEALTH AND WELLNESS AND SPIRITUAL FORMATION | SGOD | Small Value Procurement |  | JUNE 18, 2026 |  |  | JUNE 23, 2026 |  |  |  | JUNE 25, 2026 |  | JUNE 30, 2026 | JUNE 30, 2026 | GoP | 15000 | 15000 |  | 14000 | 14000 |  |  |  | MOMMY VINES CUISINE | UNPAID
| PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF CAPACITY BUILDING ON STRATEGIC PUZZLE -BASED LEARNING FOR TEACHERS | CID | Small Value Procurement |  | JUNE 18, 2026 |  |  | JUNE 23, 2026 |  |  |  | JUNE 25, 2026 |  | JULY 11, 2026 | JULY 11, 2026 | GoP | 43650 | 43650 |  | 34.920.00 | 34.920.00 |  |  |  | MOMMY VINES CUISINE | UNPAID
| PROCUREMENT OF SUPPLIES FOR THE CONDUCT OF END-OF-SCHOOL YEAR RITES OF ALS SY 2025-2026 | CID | Small Value Procurement |  | JUNE 18, 2026 |  |  | JUNE 23, 2026 |  |  |  | JUNE 25, 2026 |  | JULY 08, 2026 | JULY 08, 2026 | GoP | 1384 | 1384 |  | 1354.5 | 1354.5 |  |  |  | MFR MARKETING | UNPAID
| PROCUREMENT OF SNACKS FOR THE CONDUCT OF END-OF-SCHOOL YEAR RITES OF ALS SY 2025-2026 | CID | Small Value Procurement |  | JUNE 17, 2026 |  |  | JUNE 23, 2026 |  |  |  | JUNE 25, 2026 |  | JULY 09, 2026 | JULY 09, 2026 | GoP | 6800 | 6800 |  | 4900 | 4900 |  |  |  | DISHTURB CATERING SERVICE | UNPAID
Unprogrammed Procurement | [16 empty] | 7076478.42 | 7076478.42 | 0 | 6278687.63 | 6278687.63 | 0 | 0 | 0
Total Alloted Budget of Procurement Activities | [16 empty] | 7076478.42
Total Contract Price of Procurement Actitvites Conducted | [19 empty] | 6278687.63
Total Savings (Total Alloted Budget - Total Contract Price) | [21 empty] | 797790.79
Prepared by: | [8 empty] | Recommended for Approval: | [10 empty] | Approved
NITZTHER L. TABOTABO | [8 empty] | MARITES C. CAPILITAN, PhD | [10 empty] | PETER J. GALIMBA
BAC Secretariat | [8 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity